## Scope
Purpose | Development of an in-house training program for basic Python (focused on PySpark)
Scope | Support upskilling of Clinical Programming staff (J&J and all vendors). Developing a training academy and materials that can potentially be added to the J&J LMS system, becoming part of the role-specific training matrix.
Requirements
1 | Location of training-development staff | Europe
2 | Volume of students | 300+
3 | Location of students | Global locations
4 | Delivery of training | Online/Remotely
5 | Structure of training | Combination of online self-service and homework. Automated/recorded for delivery, with separate DU-SME led technical sessions to support continuous learning outside of the LMS
Questions
1 | Approximate timeframe for development | 6 months
Modular approach, allowing delivery of initial modules, while future modules are under development
2 | Format of training | Recorded short-duration topics, allowing pause for trainees to develop Notebook. Including quiz at end of each module. To be confirmed by J&J LMS team
3 | Training to be delivered en-masse, in cohorts, per region ? | For each new-module, small pilot cohort. Before open to all staff
4 | Will training completion come with certification | TBC
5 | Is a determination of competancy required | TBC
6 | What should students be able to do at the end (e.g. data manipulation, data pipelining) | Utilise PySpark for data manipulation (within Databricks), etc
7 | Maintenance planning | Identify J&J resources by mid-Oct to whom Simon will handover during November
References
1 | https://www.python-academy.com/courses/python_course_programmers.html | Reference to support module definition, possible topics, etc
Future considerations
1 | What support will students receive after the course in the first months of work | Mentoring from experienced programmers and Python Subject Matter Experts

## Actions
Item | Action | Assigned | Status | Due Date | Comments
1 | Process vendor approval | Graham | Complete |  | Complete 07-Apr
2 | Contract Python Consultant / Work Order | Keith/Graham | Complete |  | Complete 06-Jun
3 | Assign ICON staff | Graham | Complete |  | Complete 14-Apr
4 | Initiate regular meetings to finalise requirements and create project-plan | Keith | Complete |  | Complete 07-Apr. Scheduled and ongoing
5 | Define audience, which in turn further defines scope for Action-Item 6 | Mark | Complete |  | All C&SP staff
6 | Define scope /modules at high-level allows contracting Python Consultant | Nicolas | Complete |  | Complete 16-Apr. Agreed by team at meeting 23-Apr.
7 | Define scope /modules at detailed-level allowing development to start | Nicolas / Simon | Complete |  | Complete 18-Jul
8 | Assess ~J&J FTE requirement and assign J&J staff | Sumesh | Complete |  | Complete 09-May
9 | Confirm if Summit is the LMS to be used | Mark | Complete |  | Mark has noted that development should proceed "offline", with incorporation to LMS being reassessed at a later date.
10 | Define LMS format-requirements and any system limitations | Mark | Complete |  | Mark has noted that development should proceed "offline", with incorporation to LMS being reassessed at a later date.
11 | Python / Databricks sandbox area | Tad | Pending | 2025-07-30 | Review with David and Tad, to ensure Simon has a suitable area for development
12 | Deliver prototype of training (initial 3x core-python modules) | Lucas | Pending | 2025-09-03
13 | Deliver Core-Python module for review | Lucas | Pending | 2025-08-01
14 | Core-Python module finalised (outside of LMS) | Lucas | Pending | 2025-08-11
15 | Deliver Systems-Setup module for review | Simon/Tad/Nicolas | Pending | 2025-08-15
16 | Systems-Setup module finalised | Simon/Tad/Nicolas | Pending | 2025-08-25
17 | D4U-training - assessment of need for separate development | J&J Team | N/A | N/A | Nicolas has assessed that D4U training is required. Assessment is out-of-scope for this particular team.
18 | Branded materials for incorporation into development | Tad | Pending | 2025-07-30 | Creating a J&J appropriate style

## Modules in or out-of-scope
Draft v2.0
Priority | Module-No | Modules | Responsibility (Consultant or J&J) | In Scope ? | Learning Order | Dev Order | Delivery Date | Owner | Resource1 | Resource2 | Delivery Method | Mandatory Y/N | Loaded to LMS
| 1 | System Setup | Combined | Y | 1 | 2 | 2025-08-25 | Tad | Nicolas |  |  | Y
| 2 | Core Python | Combined | Y | 2 | 1 | 2025-08-11 | Tad | Nicolas |  |  | Y
| 3 | PySpark | Combined | Y | 3 | 3 | Sep | Tad | Nicolas |  |  | Y
| 4 | Git / Bitbucket | Combined | Y | 4 | 5 | Oct | Mark | Nicolas |  |  | Y
| 5 | Databricks | Combined | Y | 5 | 6 | Oct | Mark | Nicolas |  |  | Y
| 6 | Advanced | Combined | Y | Optional | 4 | Sep | Tad | Nicolas |  |  | N
For reference only, as Out of Scope :
| 6 | JIRA Process | J&J | N |  |  |  | Mark | Paul
| 7 | DRM | J&J | N |  |  |  | Mitul | Required ?
| 8 | D4U Overview | J&J | N |  |  |  | Mark | Ankit
| 9 | D4U Marvel Output Detail | J&J | N |  |  |  | Mark | Ankit
| 10 | D4U UI | J&J | N |  |  |  | Mark | Ankit

## Team
Name | Company | Title | Role
Sumesh Kalappurakal | J&J | Snr Dir, C&SP | LT Sponsor
Mark Bynens | J&J | Dir, Tech Sol | Project Lead
Tadeusz Lewandowski | J&J | Dir DE | DE Head
Nicolas Dupuis | J&J | Prin Tech Lead | SME
Keith Hood | ICON | Snr Dir, Biometrics | LT Sponsor
Graham Crawley | ICON | AD, Data Science | Project Lead
David Tatton | ICON | Manager, Data Science | SME
Lucas Kacem | Digital Unicorn | Project-Lead | Project-Lead
Simon Renauld | Digital Unicorn | Python Consultant | Python-expert
Jake Jay | Digital Unicorn | Python Consultant | Content-creator
Sadaf | Digital Unicorn | Copywriting | Copywriting

## Meeting Notes
Notes 07-Apr :
Scope - Nicolas' existing 4x training modules only (Basic Pandas/PySpark, and Databricks/D4U J&J specific)
Gain certificate - before independant live workload
Notes 14-Apr :
1/ consultant to assess format and delivery options for all modules
2/ assess the workload required from J&J to input to Modules 1 & 2, while also driving development of Modules 3 & 4
3/ J&J resource assessment and assignment confirmation
4/ Central documentation - support needed from Donald Paterson ? C&SP portal ?
Module-1 Pandas Consultant to review and expand. J&J to provide real-world examples
Module-2 PySpark Consultant to review and expand. J&J to provide real-world examples
Module-3 Databricks J&J to review and expand
Module-4 Data4You J&J to review and expand
Notes 23-Apr :
David Tatton introduced to the team. David oversees ICONs 25x CDAR staff (across all DUs and TechSol) and will work with Nicolas on this project.
Agreement on in-scope topics 1 to 5. With topics 6 to 10 out-of-scope for this specific Innovation Fund initiative (i.e. can be added by J&J at a later date).
Increased J&J resource required, within the Q2/Q3 timeframe and almost immediate start. Graham to provide estimate to Sumesh for review.
Actions tab - updated with a first draft of action-assignment for team review. To be reviewed by J&J, with feedback sent to Graham
Notes 29-Aug : (Nicolas, Lucas, David, Graham)
Agreed "Module-Topic List" tab is the master-list, guiding PowerPoint and Notebook creation
Agreed that delivery will flip between PP with video (delivering content) and Notebooks (covering syntax). Therefore we can develope both in tandem.
Agreed continue to focus on 2.1, 2.2 & 2.3 to finsalise PP amd Notebook prototype. Rather than 2.4 - 2.6, which are a little simpler for prototype review.
Agreed Notebook will hold the full module. Rather than Notebooks for each unique topics.
Agreed PP and Notebook also to be available for future reference, i.e. in basic format without video or audio
Current deliverable Digital-Unicorn – Prototype : Topics 2.1, 2.2 & 2.3 only. Due Mon 01-Sep: Implement feedback on PowerPoint material - Feedback on trainee experience level, duration of Topics, variable names must adhere to CDISC SDTM convention. Develop Notebooks for delivery of syntax
Request from Nicolas to add in to Advanced section, a topic contaning context around Gen AI code creation (e.g. Amazon Q) and impact to the programmers experience
Notes 01-Sep : (Nicolas, Lucas, Simon, David, Graham)
Module-Topic-List tab - Duration added to gain understanding of total duration of course. Approval-date added to track progress as individual Topics are finalised.
Current deliverable Digital-Unicorn – Prototype : Topics 2.1, 2.2 & 2.3 only. Due-date pushed out to Tue 02-Sep a.m.: Implement feedback on PowerPoint material - Feedback on trainee experience level, duration of Topics, variable names must adhere to CDISC SDTM convention. Develop Notebooks for delivery of syntax

## Overall Format
Out-of-Scope due to lack of LMS
1 | Competancy Assessment
2 | Certification
3 | Interactive Code
4 | AI Assistant
Format
1 | Brief intro video - slide alongside trainer
2 | Main content - PowerPoint with audio of trainer
3 | Python Notebooks stepthrough of syntax with audio of trainer
4 | Python Notebook developed by Trainee via excercises
5 | Quiz
6 | Quiz video with explanation, trainer in small window, bottom-right
NB/ | Options for other topics: animation; whiteboard; etc, to be advised by Digital-Unicon
Format/Content Feedback
1 | Level of detail - trainees are experienced programmers
2 | Topic average duration expected to be ~15 mins
3 | SDTM naming convention to be used